## Sheet1
|  | AWWA-2014 |  | Part B Project-Specific Milestones
Goal during project period: |  |  | 1 | 15 | 15 | 1 | 60 | 4 | 40 | 1
Timestamp | 01-Reporter | 03-Qtr ended | 20-Hire-Ambassador | 21-Ambassador-Agreements | 22-Ambassador-Deals | 23-India-Offc | 24-India-Opps | 25-Pavilions | 26-Pavilion-Exhibitors | 27-Mission-SAmerica | 40-Comments
| jjohnson@awwa.org | 2014-12-31 |  | 0 | 0 |  | 0 |  | 0 | 0 | 20-Liz Haigh hired as AWWA Ambassador23 India Office will open 1/31/201525-US/AWWA Pavilion at WETEX April 21-23.
13/07/2015 | jjohnson@awwa.org | 2015-06-30 | 0 | 0 | 0 | 0 | 0 | 1 | 10 | 5 | 20-Gay Parter DeNileon hired to replace Liz Haigh 25 WETEX US Pavilion has 9 success agreements 27- Chile and Colombia trade mission finalized for week of November 15,2016 23 - India Office - position still open for Executive Manager of India Office. 21 - 7 companies/countries were contacted regarding AWWA standards/manuals 23 - Gaurav Sood hired through MCI. Effective June 2015 25 - US/AWWA Pavilion at WETEX in Duabi April 2015. 26 - 10 companies exhibited in US/AWWA Pavilion at WETEX 27 - 5 companies have registered and signed success agreements to date
2015-02-10 | jjohnson@awwa.org | 2015-09-30 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 7 | 21-working on agreements with Kuroda in Mexico. Standards engineer attended Caribbean Water Works Association, working with attendee's on providing free standards to Caribbean utilties. 25 - two companies signed up to date for IFAT Pavilion. 27 - 7 companies signed up for the trade mission.
|  |  | 0 | 0 | 0 | 0 | 0 | 3 | 10 | 12
As a percentage of goal during period: |  |  | 0% | 0% | 0% | 0% | 0% | 75% | 25% | 1200%
Note on C1: Enter reports for one quarter on one row. Results from all reported quarters are cumulated automatically at the bottom of the report template.
Note on A3: Enter the date that you completed the report for the quarter reported.
Note on B3: Email address of person completing report.
Note on C3: A quarter comprises three months or any portion thereof ending on March 31, June 30, September 30, or December 31. Enter, e.g. June 30,2013, as 06/30/2013. It will display as 2013.06.30.
Note on D3: Hire one 3-year contract employee to identify and facilitate partnerships in target markets with U.S. firms. [Goal: 1]
Note on E3: Broker agreements that lead to U.S. exports with companies or other organizations doing business in target markets. [Goal: 15 agreements]
Note on F3: Establish deals that lead to U.S. exports. Deals will be with target-market entities for such activities as publication, sponsorship, and distribution. [Goal: 15 deals]
Note on G3: Establish an India office staffed by an AWWA employee or contractor. [Goal: 1]
Note on H3: India office will develop 2 potential sale opportunities per month. (2 * 30 = 60). [Goal: 60]
Note on I3: Host U.S. pavilion at 4 trade shows. [Goal: 4]
Note on J3: Instances of a U.S. firm able to export exhibiting at a U.S. pavilion. [Goal: 40]
Note on K3: Week-long trade mission by executives of export-able U.S. firms. Target markets will almost certainly include Brazil, and probably Colombia and Peru, but may be composed of other S. American markets. [Goal: 1]
Note on L3: If you need to explain any of the numbers reported in fields 20-27 enter text here preceded by the field number to which the comment pertains.

## QuarterEnded
2014-12-31
2015-03-31
2015-06-30
2015-09-30
2015-12-31
2016-03-31
2016-06-30
2016-09-30
2016-12-31
2017-03-31
2017-06-30
2017-09-30
2017-12-31
2018-03-31
2018-06-30
2018-09-30
2018-12-31
2019-03-31
2019-06-30
2019-09-30
2019-12-31