## Sheet1
|  | DUSBDC-2014 |  |  |  | Part B Project-Specific Milestones
Goal during project period: |  |  | 30 | 20 | 20 | 24 | 480 | 300 | 3000 | 3 | 30 | 20 | 10000000
Timestamp | 01-Reporter | 03-Qtr ended | 20-US Firms-to-Col | 21-US Firms-to-Chile-or-Peru | 22-US Firms-to-Mex | 23-Export-Sem | 24-US-Partic-Export-Sem | 25-Sem-Partic | 26-Web-Hits | 27-Reverse-Missions | 28-For-Partic-Reverse-Missions | 29-US-Firms-Assisted-Non-Mission | 30-Export-Fin | 40-Comments
2015-01-29 | mckinney@duq.edu | 2014-12-31 | 0 | 0 | 0 | 5 | 15 | 0 | 25 | 0 | 0 | 4 | 0 | 29 We have spent the first 3 months planning for our trade mission to Colombia and Mexico. There were some issues with the Mexican US DOC embassy that delayed our being able to finalize trade mission dates, prices, etc. which were not resolved until mid-January, 2015. These delays resulted in our not being able to widely promote our activities through seminars and webinars as we had planned. Our website went live in January, 2015. We have planned seminars and webinars for 2015 and expect that we will gain clients and sales. We have started to recruit clients and assist them with information about the Pacific Alliance markets, list of tradeshows new Mexican energy reforms for the oil and gas industry. We assisted four in the 1st quarter and some may attend the trade missions.
2015-04-30 | mckinney@duq.edu | 2015-03-31 |  |  |  | 6 | 110 | 0 | 250 | 0 | 0 | 30 | 50000 | During this quarter we have been very busy holding seminars and visiting companies to recruit for the June trade mission to Mexico and Colombia. Several firms were visited and assisted through our consulting to determine market access opportinities for them to the Pacific Alliance countries.
2015.07.31 | mckinney@duq.edu | 2015-06-30 | 1 | 1 |  | 4 | 200 |  | 363 | 1 | 20 | 5 | 0 | Due to intense competition and pricing differentials, we postpooned the planned mission to Colombia and Mexico to Spring, 2016. We have been recruiting for the Trade Show in Chile and interacting with the US Embassy in Chile as well as Peru and our local USEAC personnel. As of July, the booth slots are filled for the October ConExpo Trade Show.
2015.10.30 | mckinney@duq.edu | 2015-09-30 |  | 0 |  | 1 | 42 | 25 | 600 | 0 | 0 | 2 |  | This quarter we recruited and prepared the companies to attend the ConEXPO Latin America trade show in Chile in October. We recruited 4 firms to go and 4 catalogue companies.
|  |  | 1 | 1 | 0 | 16 | 367 | 25 | 1238 | 1 | 20 | 41 | 50000
As a percentage of goal during period: |  |  | 3.333% | 5% | 0% | 66.67% | 76.46% | 8.333% | 41.27% | 33.33% | 66.67% | 205% | 0.5%
Note on C1: Enter reports for one quarter on one row. Results from all reported quarters are cumulated automatically at the bottom of the report template.
Note on A3: Enter the date that you completed the report for the quarter reported.
Note on B3: Email address of person completing report.
Note on C3: A quarter comprises three months or any portion thereof ending on March 31, June 30, September 30, or December 31. Enter, e.g. June 30,2013, as 06/30/2013. It will display as 2013.06.30.
Note on D3: Number of U.S. businesses able to export that visit Colombia. Count each company only once--first visit only to this market. [Goal:30]
Note on E3: Number of U.S. businesses able to export that visit Chile or Peru. Count each company only once--first visit only to either market. [Goal:20]
Note on F3: Number of U.S. businesses able to export that visit Mexico. Count each company only once--first visit only to this market. [Goal:20]
Note on G3: Eigh t(8) export seminars are planned each year for a project total of 24. [Goal: 24]
Note on H3: Instances of an individual partcipating in each export seminar should average 20, for a total of 480 for the project [Goal: 480]
Note on I3: Instances of an individualaccessing an online webinar @ 100 per year. [Goal: 300]
Note on J3: Website portal hits@ 1000/yr. [Goal: 3,000]
Note on K3: Reverse trade mission@ 1/yr. [Goal: 3]
Note on L3: Instances of a non-U.S. buyer partcipating in a reverse mission @ 10/mission. [Goal: 30]
Note on M3: Number of U.S. firms assisted that did not participate in an outbound trade mission. [Goal: 20]
Note on N3: Export financing arranged. [Goal: $10,000,000]
Note on O3: If you need to explain any of the numbers reported in fields 20-30 enter text here preceded by the field number to which the comment pertains.

## QuarterEnded
2014-12-31
2015-03-31
2015-06-30
2015-09-30
2015-12-31
2016-03-31
2016-06-30
2016-09-30
2016-12-31
2017-03-31
2017-06-30
2017-09-30
2017-12-31
2018-03-31
2018-06-30
2018-09-30
2018-12-31
2019-03-31
2019-06-30
2019-09-30
2019-12-31