## Sheet1
|  |  |  | EBPA-2012 |  |  | Project Perfomance Report (PPR) Part B -Cumulative
Goal during project period: |  |  | 6 | 84 | 3 | 30 | 1500 | 3300 | 450
Timestamp | 01-Reporter | 03-Qtr ended | 20-Trade missions | 21-US firms on trade missions | 22-Reverse missions | 23-China reverse mission partici-pants | 24-New China contacts | 25-China partici-pants in mission | 26-Assists to US firms | 27-China code modifi-cations | 40-Comments
| rbraden@ep.org | 2013-06-30 | 1 | 11 | 0 | 0 | 421 | 421 | 15 | 0 | Reverse trade mission postponed: Lead Chinese company representative injury prevented travel by his company members, which was half of the group.
| rbraden@ep.org | 2013-12-31 | 1 | 9 | 0 | 0 | 200 | 200 | 20 | 0
2012.11.01 | rbraden@u.washington.edu | 2013 Mar 31 | 0 | 0 | 0 | 0 | 100 | 0 | 10 | 0 | Quarter spent preparing for April 2013 China sales mission.
| rbraden@ep.org | 2014 mar 31 | 0 | 9 | 0 | 0 | 200 | 0 | 25 | 0 | Quarter spent recruiting and preparing for May 2014 mission
| rbraden@ep.org | 2014 June 30 | 1 | 10 | 0 | 0 | 251 | 0 | 50 | 0 | Quarter spent recruiting and preparing for May 2014 mission
| rbraden@ep.org | 2014 Sept 30 | 0 | 0 | 0 | 0 | 10 | 0 | 40 | 2 | 1. China Timber Structure Design Code - The second round of revision has been completed. The revision was submitted to the China Ministry of Construction and is awaiting approval. 2. Shanghai Engineered Wood Structure Design Code - The draft was completed and is pending a public hearing.
| rbraden@ep.org | 2014 Dec 31 | 1 | 7 | 0 | 100 | 50 |  | 20 | 2 | Code progress noted on Part A progress report. Staff spent quarter planning June 2015 reverse mission
| rbraden@ep.org | 2015 Mar 31 | 0 | 0 | 0 | 0 | 30 | 0 | 15 | 0 | Preparation for June 2015 inbound mission - postponed due to Visa issue among some China applicants. Rescheduled inbound mission for Sept 21-27, 2015 and continued with recruiting in China.
| rbraden@ep.org | 2015 June 30 | 0 | 0 | 0 | 0 | 20 | 0 | 5 | 0 | Preparation for Sept 2015 inbound buyers' mission and November 2015 outbound China Mission
| rbraden@ep.org | 2015 Sept 30 | 0 | 0 | 1 | 12 | 25 | 0 | 25 | 0 | Lead a group of 8 Chinese, 2 Thai, and 1 Malaysian softwood lumber importers. The group also included the Shanghai editor for Furniture and Panels China magazine who provided press coverage for the event and the USCB program. Quarter also included recruiting and preparation for the November 14-18, 2015 China Trade Mission.
Sum for project period: |  |  | 4 | 46 | 1 | 112 | 1307 | 621 |  | 4
As a percentage of goal during period: |  |  | 66.67% | 54.76% | 33.33% | 373.3% | 87.13% | 18.82% | 0% | #DIV/0!
Note on E1: Report results only for the current quarter. DO NOT CUMULATE RESULTS FROM PREVIOUS QUARTERS. Part B below is for reporting performance on measures designed by EBPA specific to its 2012 MDCP project. Note that performance on ITA's primary metric, exports, is NOT reported in Part B. Report separately each quarter in Part A: field 6-export transations (goal for 2012.11.01-2015.10.31 is $400,000,000). Enter ONLY NUMBERS in fields 20-27 below. NOTES regarding numbers entered in fields 20-27 can be entered in field 40-Comments.
Note on A4: Enter the date that you completed the report for the quarter reported.
Note on B4: Email address of person completing report.
Note on C4: A quarter comprises three months or any portion thereof ending on March 31, June 30, September 30, or December 31. Enter, e.g. June 30,2013, as 06/30/2013. It will display as 2013.06.30.
Note on D4: Each trade mission to target three cities per mission. Goal: 6 (2 missions per year)
Note on L4: If you need to explain any of the numbers reported in fields 20-27 enter text here preceded by the field number, e.g. "27-Fire code modified to allow gypsum board."
Note on E4: Each time a U.S. company participates in an outbound trade mission to China. Goal: 84 (14 firms x 6 missions)
Note on F4: Inbound missions of China buyers to U.S. Goal: 3 (one year)
Note on G4: China architects or buyers that come to U.S. on missions. Goal: 30 (10 per mission)
Note on H4: Number of new China contacts with potential to result in export sales or distributorships for U.S. companies. Goal: 1500 (500 per year)
Note on I4: Number of China participants in trade missions. Goal: 3300 (1100 per year)
Note on J4: Each instance where US-ChinaBuild helps a U.S. firm with market information, business referrals, or development of business plans. Goal: 450 (150 per year)
Note on K4: Each US-ChinaBuild-affected change in China inspection code, building code, or product standard that expands the use of U.S. building materials.