## Sheet1
|  |  |  | IFTA-2010 |  | Project Perfomance Report (PPR) Part B
Goal during project period: |  |  | 90 | 3600 | 900 | 144 | 300 | 8 | 108000 | 90
Timestamp | 01-Reporter | 03-Qtr ended | 20-US exhibit-ors in Am Pavilion | 21-Mtgs for US exhibit-ors | 22-Instances of US firms listing in catalog | 23-US exhibi-tor satis-cation surveys done | 24-Foreign buyer satis-faction surveys done | 25-Media mentions | 26-Mktg campaign emails | 27-US exhibit-ors reporting | 28-Campaign for buyers | 40-Comments
2011-02-02 15:30 | ssheik@ifta-online.org | 2010.12.31 | 0 | 0 | 0 | 0 | 0 | 4 | 0 | 0
2011-05-09 15:47 | ssheik@ifta-online.org | 2011.03.31 | 22 | 660 | 195 | 0 | 0 | 10 | 16500 | 22 |  | For Item 23, we plan to follow up with Participants to have them fill out the evaluation. We are currently working with the team to ID proper evaluation questions. For item 24, we realized that buyer evaluations on site was no practical. We are working with the team to identify any alternative goal(s).
2011-08-15 15:31 | ssheik@ifta-online.org | 2011.06.30 |  |  | 195 |  |  | 0 |  |  |  | Follow up Pavilion evaluations and exhibitor reports in items 23 & 27 are being conducted by the ITA team members. After further consideration, it appears that the buyer evaluations (at least from teh IFTA side alone) are not as practical/feasible as originally thought. We will review this and other goals with the ITA team on the next conference call for the upcoming hosted buyer program for AFM 2011.
02.24.12 | ssheik@ifta-online.org | 2011.09.31 | [9 empty] | During this period, after discussions with ITA, we decided to amend the award activities from applying the MDCP award to an American Pavilion at DISCOP to instead support a Hosted-Buyer program at American Film Market 2011 which took place in Nov. 2011.
02.24.2012 | ssheik@ifta-online.org | 2011.12.31 | 12 | 200 |  |  |  | 3 | 5000 |  | 5000 | The responses here are in the context of buyers that participated in the hosted buyer program at AFM 2011. 22-We had 12 buyers participate in the subsidized hotels, and we worked with the commercial service delegates to combine resources to market to buyers and coordinate meetings with exhibitors.
2012-05-21 18:48 | ssheik@ifta-online.org | 2012.03.31 | 30 | 900 | 300 |  |  | 6 | 2 |  |  | Re item 23- Our Pavilion head Natasha Berechko is in Cannes. When she returns, I will inquire re the status of pavilion evaluations. Re item 26- 2 email blasts to buyers. Re item 27, our MDCP partner in Commerce collects the reports from Exhibitors and provides this information in Part A reports. Re item 24- we determined that having buyers fill out evaluations was not systematically practical and convinient for buyers.
2012-07-05 15:57 | ssheik@ifta-online.org | 2012.06.30 |  |  | 150 |  |  | 4 |  |  |  | There was no Pavilion in this Quarter. Numbers and information apply to run-off activity this quarter from FILMART conducted and reported on in the previous quarter.
2012-10-24 15:51 | ktommaselli@ifta-online.org | 2012.09.30 | N/A | N/A | 170 |  |  | 0 | 24400 | N/A |  | Re 20 & 21- There was no Pavilion during this Quarter. Re item 23 & 24- we determined that having buyers fill out evaluations was not systematically practical or convenient for buyers. Re item 26- Numbers and information apply to marketing activities conducted for the upcoming 2012 American Film Market in which 4 email blasts were sent to buyers. Re item 27- our MDCP partner in Commerce collects the reports from Exhibitors and provides this information in the Part A report
2013-01-29 13:21 | ktommaselli@ifta-online.org | 2012.12.31 | 51 | 53 | 200 |  |  | 1 | 43000 |  |  | The responses here are in the context of buyers that participated in the hosted buyer program at AFM 2012. 20- Of the 51 IBP buyers, 11 buyers participate in the subsidized hotels, and we worked with the commercial service delegates to combine resources to market to buyers and coordinate meetings with exhibitors. Even though some of the buyers in the delegation did not stay in MDCP/IFTA hotels, the MDCP package was marketed to all of the buyers which definitely contributed to their decision to attend AFM 2012. Evaluations and follow up with buyers and exhibitors is conducted by Andrea DaSilva.
2013.07.29 | kmeltzer@ifta-online.org | 2013.06.30 | N/A | N/A | 150 | N/A | N/A | 4 | N/A | N/A |  | There was no Pavilion in this Quarter. Numbers and information apply to run-off activity this quarter from FILMART conducted and reported on in the previous quarter.
2013.10.17 | kmeltzer@ifta-online.org | 2013.09.30 | N/A | N/A | 180 |  |  | 0 | 40000 | N/A |  | Re 20 & 21- There was no Pavilion during this Quarter. Re item 23 & 24- we determined that having buyers fill out evaluations was not systematically practical or convenient for buyers. Re item 26- Numbers and information apply to marketing activities conducted for the upcoming 2013 American Film Market in which email blasts were sent to buyers. Re item 27- our MDCP partner in Commerce collects the reports from Exhibitors and provides this information in the Part A report.
2014.01.30 | ecady@ifta-online.org | 2013.12.31 | N/A | N/A | 200 | N/A | N/A | N/A | 45000 | N/A | N/A | These responses are for buyers who participated in the Hosted Buyer Program at the 2013 AFM in November. Of the 35 IBP buyers, 7 buyers participated in the subsidized hotels. We worked with the commercial service delegates to combine resources to market to buyers and coordinate meetings with exhibitors. Even though some of the buyers in the delegation did not stay in MDCP/IFTA subsidized hotels, the MDCP package was marketed to all of the buyers which definitely contributed to their decision to attend AFM 2013. Evaluations and follow up with buyers and exhibitors are conducted by Andrea DaSilva. Notes: Re 20 & 21 - There was no Pavilion during this Quarter. Re item 23 & 24 – As in past years, we determined that having buyers fill out evaluations was not systematically practical or convenient for buyers. Re item 26 - Numbers and information apply to marketing activities conducted for the 2013 American Film Market in which email blasts were sent to buyers. Re item 27 - our MDCP partner in Commerce collects the reports from Exhibitors and provides this information in the Part A report.
2014.04.30 | ecady@ifta-online.org | 2014.03.31 | 36 | N/A | 400+ | N/A | N/A | 3 | 20000 | N/A | 20000 | Re items 21, 23 and 27 - our MDCP partner in Commerce collects the reports from Exhibitors and also provides this information in Part A of the quarterly progress report. Re item 24 - we determined that having buyers fill out evaluations was not systematically practical and inconvenient for buyers.
2014.07.30 | kmeltzer@ifta-online.org | 2014.06.30 | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A
Sum for project period: |  |  | 151 | 1813 | 1740 | 0 | 0 | 35 | 193902 | 22 | 25000
As a percentage of goal during period: |  |  | 167.8% | 50.36% | 193.3% | 0% | 0% | 437.5% | 179.5% | 24.44% | #DIV/0!
Note on E1: For Part B below report on performance measures unique to your project. Do not cumulate the results from previous quarters. Report only the results from the quarter you select below. (Part A is where you will report your progress on your goal of generating $122 m in exports.)
Note on A4: Enter the date that you completed the report for the quarter reported.
Note on B4: Email address of person completing report.
Note on C4: A quarter comprises three months or any portion thereof ending on March 31, June 30, September 30, or December 31. Enter, e.g. June 30,2013, as 06/30/2013. It will display as 2013.06.30.
Note on M4: Enter any comments regarding any of the numeric responses above. E.g. "27-Includes 5 U.S. exhibitors that did not report until 3 weeks after the event." (Comments are NOT required.) Supplemental documentation of quarterly activity such as published studies, event fliers, and photos can be emailed separately to Brad.Hess@trade.gov.
Note on D4: Instances of a U.S. firm exhibiting in the American Pavilion at FIMART. 1st year: 20, 2nd year: 30, 3rd year: 40 = Goal: 90.
Note on F4: Instances of U.S. firms marketing their products on IFTA's "TheFilmCatalogue.com" 300 (annually) x 3 years = Goal: 900.
Note on E4: Meeting count. For each exhibiting company at every American Pavilion, ensure at least 40 pre-scheduled "meetings of substance," i.e., a sit-down, one-on-one discussion with international buyers. 20 x 40 + 30 x 40 + 40 x 40 = Goal: 3,600
Note on G4: Pavilion evaluations. Surveys completed by U.S. exhibitors on exhibitor satisfaction, pavilion effectiveness, suggestions for future pavilions, effect on sales, etc. 1st yr: 32, 2nd yr: 48, 3rd yr: 64 = Goal: 144
Note on I4: Articles and other features where the project is noted in industry media such as The Hollywood Reporter, Variety, and Screen Digest. 1st yr: 4, 2nd yr: 2, 3rd yr: 2 = Goal 8
Note on J4: Advance email marketing campaigns to foreign buyers. Number of promotional email campaigns to foreign buyers for exhibiting U.S. firms. Three (3) emails to 6,000 buyers per event x 6 events = Goal: 108,000 emails.
Note on K4: U.S. exhibitors submitting reporting documents within 2 weeks of the event. Goal: 90. (Compare to 20-Pav exhibitors)
Note on H4: Pavilion evaluations. Surveys completed by foreign buyers on pavilion effectiveness, suggestions for future pavilions, effect on sales, etc. 50 per pavilion = Goal: 300