## Sheet1
|  | ACA-2015 | Part B Project-Specific Milestones
Goal during project period: |  |  | 6 | 300
Timestamp | 01-Reporter | 03-Qtr ended | 20-Trade-Missions | 21-Mtgs-1on1-AAPEX | 40-Comments
2016-01-29 | angela.chiang@autocare.org | 2015-12-31 | 0 | 0 | For 2016, we have the following two trade missions scheduled: Peru (May 17-19) and Guatemala/El Salvador (June 21-22). One-on-One meetings at AAPEX will take place in November 2016.
2016-05-26 | angela.chiang@autocare.org | 2016-03-31 | 0 | 0 | For 2016, we have the following two trade missions scheduled: Peru (May 17-19) and Guatemala/El Salvador (June 21-22). One-on-One meetings at AAPEX will take place in November 2016.
2016-08-08 | angela.chiang@autocare.org | 2016-06-30 | 2 | 0 | Trade missions to Peru (May 2016) and Guatemala (June 2016) have been completed. One-on-One meetings at AAPEX will take place in November 2016.
2016-11-21 | angela.chiang@autocare.org | 2016-09-30 | 0 | 0 | One-on-One meetings were completed at AAPEX early November and will be reported in next quarterly report.
2017-02-06 | angela.chiang@autocare.org | 2016-12-31 | 0 | 25 | Twenty-five one-on-One meetings were completed at AAPEX in November 2016.
2017-05-30 | angela.chiang@autocare.org | 2017-03-31 | 0 | 0 | For 2017, we have the following two trade missions scheduled: Colombia (June 7-8) and Honduras/Nicaragua (Sept. 26/28). One-on-One meetings at AAPEX will take place in November 2017.
2017-08-30 | angela.chiang@autocare.org | 2017-06-30 | 1 | 0 | Trade mission to Colombia (June 7-8) was completed.
2017-11-29 | angela.chiang@autocare.org | 2017-09-30 | 1 | 0 | Trade mission to Honduras and Nicaragua (Sept. 26-28) was completed.
2018-02-18 | angela.chiang@autocare.org | 2017-12-31 | 0 | 60 | Sixty one-on-one meetings were completed at AAPEX in November 2017.
2018-04-30 | angela.chiang@autocare.org | 2018-03-31 | 0 | 0 | For 2018, we have the following two trade missions scheduled: Costa Rica (May 21-22) and Chile (Aug. 21-22). One-on-One meetings at AAPEX will take place in October 2018.
2018-08-14 | angela.chiang@autocare.org | 2018-06-30 | 1 | 0 | Trade mission to Costa rica (May 21-22) was completed.
2018-11-30 | angela.chiang@autocare.org | 2018-09-30 | 1 | 0 | Trade mission to Chile (Aug. 21-22) was completed.
2019-02-28 | angela.chiang@autocare.org | 2018-12-31 | 0 | 40 | Forty one-on-one meetings were completed at AAPEX in November 2018.
2019-06-03 | angela.chiang@autocare.org | 2019-03-31 | 0 | 0 | Trade mission to Colombia is scheduled for June 5-6, 2019.
2019-09-01 | angela.chiang@autocare.org | 2019-06-30 | 1 | 0 | Trade mission to Colombia (June 5-6) was completed.
2019-12-17 | angela.chiang@autocare.org | 2019-09-30 | 0 | 0 | Currently planning one-on-one meetings at AAPEX in November 2019.
2020-01-01 | angela.chiang@autocare.org | 2019-12-31 | 0 | 65 | Conducted 65 one-on-one international matchmaking meetings at trade show AAPEX in November 2019.
2020-04-01 | angela.chiang@autocare.org | 2020-03-31 | 1 | 0 | Trade mission to Peru originally scheduled for March 16-17 was canceled due to COVID-19; participants' meetings were shifted to virtual meetings. One-on-one meeting at AAPEX (November 2020) are currently moving forward as scheduled.
2020-07-01 | angela.chiang@autocare.org | 2020-06-30 | 0 | 0 | One-on-one meeting at AAPEX (November 2020) are currently moving forward as scheduled.
2020-10-19 | angela.chiang@autocare.org | 2020-09-30 | 0 | 0 | International buyers one-on-one matchmaking program is canceled due to trade shift to virtual platform.
2020-12-04 | angela.chiang@autocare.org | 2020-12-31 | 0 | 0 | International buyers one-on-one matchmaking program is canceled due to trade shift to virtual platform. (Note the quarter end date selected is 12/31/2020 but ACA-2015 ended 11/30/2020.
2021-03-30 | angela.chiang@autocare.org | 2021-03-31 | 0 | 0 | No activities were planned or executed in the first quarter of 2021.
|  |  | 8 | 190
As a percentage of goal during period: |  |  | 133.3% | 63.33%
Note on C1: Enter reports for one quarter on one row. Results from all reported quarters are cumulated automatically at the bottom of the report template.
Note on A3: Enter the date that you completed the report for the quarter reported.
Note on B3: Email address of person completing report.
Note on C3: A quarter comprises three months or any portion thereof ending on March 31, June 30, September 30, or December 31. Enter, e.g. June 30,2013, as 06/30/2013. It will display as 2013.06.30.
Note on D3: Lead two trade missions per year to a target market. [Goal: 6 missions]
Note on E3: Identify 20 foreign buyers and broker 5 one-on-one meetings with each of the foreign buyers at each AAPEX show. [Goal: 300 (3 shows x 20 buyers x 5 mtgs)]
Note on F3: If you need to explain any of the numbers reported in fields 20-21 enter text here preceded by the field number to which the comment pertains.

## QuarterEnded
2015-12-31
2016-03-31
2016-06-30
2016-09-30
2016-12-31
2017-03-31
2017-06-30
2017-09-30
2017-12-31
2018-03-31
2018-06-30
2018-09-30
2018-12-31
2019-03-31
2019-06-30
2019-09-30
2019-12-31
2020-03-31
2020-06-30
2020-09-30
2020-12-31
2021-03-31
2021-06-30
2021-09-30
2021-12-31
2022-03-31