## Sheet1
|  |  |  | EBPA-2012 |  |  | Project Perfomance Report (PPR) Part B -Cumulative
Goal during project period: |  |  | 6 | 84 | 3 | 30 | 1500 | 3300 | 450
Timestamp | 01-Reporter | 03-Qtr ended | 20-Trade missions | 21-US firms on trade missions | 22-Reverse missions | 23-China reverse mission partici-pants | 24-New China contacts | 25-China partici-pants in mission | 26-Assists to US firms | 27-China code modifi-cations | 40-Comments
| rbraden@ep.org | 2013-06-30 | 1 | 11 | 0 | 0 | 421 | 421 | 15 | 0 | Reverse trade mission postponed: Lead Chinese company representative injury prevented travel by his company members, which was half of the group.
| rbraden@ep.org | 2013-12-31 | 1 | 9 | 0 | 0 | 200 | 200 | 20 | 0
2012.11.01 | rbraden@u.washington.edu | 2013 Mar 31 | 0 | 0 | 0 | 0 | 100 | 0 | 10 | 0 | Quarter spent preparing for April 2013 China sales mission.
| rbraden@ep.org | 2014 mar 31 | 0 | 9 | 0 | 0 | 200 | 0 | 25 | 0 | Quarter spent recruiting and preparing for May 2014 mission
| rbraden@ep.org | 2014 June 30 | 1 | 10 | 0 | 0 | 251 | 0 | 50 | 0 | Quarter spent recruiting and preparing for May 2014 mission
| rbraden@ep.org | 2014 Sept 30 | 0 | 0 | 0 | 0 | 10 | 0 | 40 | 2 | 1. China Timber Structure Design Code - The second round of revision has been completed. The revision was submitted to the China Ministry of Construction and is awaiting approval. 2. Shanghai Engineered Wood Structure Design Code - The draft was completed and is pending a public hearing.
| rbraden@ep.org | 2014 Dec 31 | 1 | 7 | 0 | 0 | 50 |  | 20 | 2 | Code progress noted on Part A progress report. Staff spent quarter planning June 2015 reverse mission
| rbraden@ep.org | 2015 Mar 31 | 0 | 0 | 0 | 0 | 30 | 0 | 15 | 0 | Preparation for June 2015 inbound mission - postponed due to Visa issue among some China applicants. Rescheduled inbound mission for Sept 21-27, 2015 and continued with recruiting in China.
| rbraden@ep.org | 2015 June 30 | 0 | 0 | 0 | 0 | 20 | 0 | 5 | 0 | Preparation for Sept 2015 inbound buyers' mission and November 2015 outbound China Mission
| rbraden@ep.org | 2015 Sept 30 | 0 | 0 | 1 | 12 | 25 | 12 | 25 | 0 | Lead a group of 8 Chinese, 2 Thai, and 1 Malaysian softwood lumber importers. The group also included the Shanghai editor for Furniture and Panels China magazine who provided press coverage for the event and the USCB program. Quarter also included recruiting and preparation for the November 14-18, 2015 China Trade Mission.
| rbraden@ep.org | 2015 Dec 31 | 1 | 9 | 0 | 0 | 110 | 100 | 30 | 1 | Lead a group of 9 US softwood lumber suppliers on a trade mission to Beijing, Tianjin, and Guangzhou, China. The mission resulted in $1.5 million in sales within weeks of completing the mission. Policy Work: USCB China staff are participating on the Ministry of Construction Building Code Committee to update the now ten year old wood frame building code. They are working with representatives from Canada and Europe to ensure that the new edition incorporates grades and species from the U.S., Canada, and Europe. The next code committee meeting is in March 2016.
| rbraden@ep.org | 2016 Mar 31 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Due to China's housing market decline, we were not able to fill an outbound mission. Started work on a fall 2016 inbound buyer's mission
| rbraden@ep.org | 2016 June 30 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Recruiting and coordination for August 2016 inbound buyers' mission.
| rbraden@ep.org | 2016 Sept 30 | 0 | 50 | 1 | 7 | 50 | 7 | 50 | 1 | Led inbound buyers' mission with 7 participants from China and one from Thailand during on August 10-18, 2016. The tour included visits with lumber mills, treaters, and remanufacturers and receptions with suppliers. Sales reported in quarterly report Part A.
| rbraden@ep.org | 2016 Dec 31 | 1 | 7 | 0 | 0 | 80 | 64 | 15 | 0 | Led a group of seven companies on a trade mission to China during the week of November 13, 2016 to Taicang, Dongguan, and Guangzhou. Sixty four Chinese buyers attendeed two receptions and the group met with additional buyers at their facilities.
| rbraden@ep.org | 2017 Mar 31 | 0 | 60 | 1 | 5 | 15 | 0 | 4 | 0 | Led inbound buyers' mission with 7 participants from China during on March 1-8, 2017 to Portland, OR and New Orleans, LA. The tour included visits with lumber mills, treaters, and remanufacturers and receptions with suppliers. Sales reported in quarterly report Part A.
| rbraden@ep.org | 2017 June 30 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Rescruitig for November 2017 China mission and planning underway
| rbraden@ep.org | 2017 Sept 30 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 0 | Rescruitig for November 2017 China mission and March 2018 China lumber buyers' mission.
| rbraden@ep.org | 2017 Dec 31 | 1 | 10 | 0 | 0 | 100 | 0 | 4 | 1 | Held November 2017 China mission. The revised GB50005 was approved by MoHURD in November and just released in December. The new version incorporated the design value for the U.S. structural timber as well as revised design value for southern yellow pine based upon the updated design value developed by SPIB. Following the release of GB50005, the code committee is in the process of developing Timber Structure Design Manual, which will be used by architects and engineers as one of the key tools in design work. The development work is involved in by the industry representatives from the U.S., Canada, New Zealand, EU and Japan. The development work is expected to be completed in the end of this year.
| rbraden@ep.org | 2018 March 31 | 0 | 0 | 1 | 8 | 50 | 8 | 6 | 0 | Held inbound China buyer
| rbraden@ep.org | 2018 Jun 30 | 0 | 0 |  | 0 | 20 | 0 | 10 |  | Planning and recruiting for November 2018 China mission and association held a seminar about US export/import trading environment featuring ITA MDCP team leader. Produced a draft itinerary and proposal for a September 2018 inbound mission request from an association of lumber and building materials importers/distributors. US Tariffs on Chinese goods resulted in the group postponing planning on the trip.
Sum for project period: |  |  | 7 | 182 | 4 | 32 | 1732 | 812 |  | 7
As a percentage of goal during period: |  |  | 116.7% | 216.7% | 133.3% | 106.7% | 115.5% | 24.61% | 0% | #DIV/0!
Note on E1: Report results only for the current quarter. DO NOT CUMULATE RESULTS FROM PREVIOUS QUARTERS. Part B below is for reporting performance on measures designed by EBPA specific to its 2012 MDCP project. Note that performance on ITA's primary metric, exports, is NOT reported in Part B. Report separately each quarter in Part A: field 6-export transations (goal for 2012.11.01-2015.10.31 is $400,000,000). Enter ONLY NUMBERS in fields 20-27 below. NOTES regarding numbers entered in fields 20-27 can be entered in field 40-Comments.
Note on A4: Enter the date that you completed the report for the quarter reported.
Note on B4: Email address of person completing report.
Note on C4: A quarter comprises three months or any portion thereof ending on March 31, June 30, September 30, or December 31. Enter, e.g. June 30,2013, as 06/30/2013. It will display as 2013.06.30.
Note on D4: Each trade mission to target three cities per mission. Goal: 6 (2 missions per year)
Note on L4: If you need to explain any of the numbers reported in fields 20-27 enter text here preceded by the field number, e.g. "27-Fire code modified to allow gypsum board."
Note on E4: Each time a U.S. company participates in an outbound trade mission to China. Goal: 84 (14 firms x 6 missions)
Note on F4: Inbound missions of China buyers to U.S. Goal: 3 (one year)
Note on G4: China architects or buyers that come to U.S. on missions. Goal: 30 (10 per mission)
Note on H4: Number of new China contacts with potential to result in export sales or distributorships for U.S. companies. Goal: 1500 (500 per year)
Note on I4: Number of China participants in trade missions. Goal: 3300 (1100 per year)
Note on J4: Each instance where US-ChinaBuild helps a U.S. firm with market information, business referrals, or development of business plans. Goal: 450 (150 per year)
Note on K4: Each US-ChinaBuild-affected change in China inspection code, building code, or product standard that expands the use of U.S. building materials.