## Sheet1
IAPMO-2013
Goal during project period: |  |  | 4 | 28 | 1800 | 130 | 108 | 10
Timestamp | 01-Reporter | 03-Qtr ended | 20-Major-Jurisdictions-adopting-UPC-ID | 21-Schools-doing-PEEP-training | 22-PEEP-graduates | 23-Products-certified | 24-US-products-certified | 25-major-US-standards-incorporated | 40-Comments
2014-01-30 | christopher.lindsay@iapmo.org | 2013.12.31 | 0 | 0 | 0 | 0 | 0 | 0 | 21 - Discussions are ongoing with several institutions
2014.03.18 | christopher.lindsay@iapmo.org | 2014.03.31 | 0 | 0 | 0 | 0 | 0 | 0 | 21 - Rather than pursue offering industry recognized personnel certifications as originally intended, IAPMO is now working with the government's construction accreditation body to develop the government accredited curriculum to the new standard.
2014.07.10 | christopher.lindsay@iapmo.org | 2014.06.30 | 0 | 0 | 0 | 0 | 0 | 0 | 21 - IAPMO is in ongoing discussions with the government's construction accreditation body to develop the government accredited curriculum to the new standard.
2014.10.20 | christopher.lindsay@iapmo.org | 2014.09.30 | 0 | 5 | 0 | 0 | 0 | 0 | 21-IAPMO signed MOU with 5 universities this past quarter to begin developing PEEP related training
2015.01.20 | christopher.lindsay@iapmo.org | 2014.12.31 | 0 | 0 | 0 | 0 | 0 | 0 | 25-The new standard or code referencing the US standards identified for this project is currently out for public commment. It appears that it will be finalized in Spring 2015.
2015.04.20 | christopher.lindsay@iapmo.org | 2015.03.31 | 0 | 0 | 0 | 0 | 0 | 10 | 25 - The new SNI for Plumbing has been officially released. The major US developed, internationally recognized standards, were incoporated into the new SNI.
2015.07.20 | christopher.lindsay@iapmo.org | 2015.06.30 | 0 | 0 | 0 | 0 | 0 | 0 | 23 - IAPMO is working with BKPN on receiving the appropriate licensing to operate a laboratry facility in Indoneisa.
2015.10.20 | christopher.lindsay@iapmo.org | 2015.09.30 | 0 | 0 | 0 | 0 | 0 | 0 | 22 - IAPMO continues to make great progress with Ministry officials in mandating the training of regulators and trained personnel on the new standard. 23 - IAPMO received approval from BKPM to move forward with its efforts on product testing this quarter. 24 - IAPMO received approval from BKPM to move forward with its efforts on product testing this quarter.
2016.01.20 | christopher.lindsay@iapmo.org | 2015.12.31 | 0 | 0 | 0 | 0 | 0 | 0 | 22 - IAPMO successfully held its first Train the Trainer session sponsored by government ministries this past quarter. Additionally, IAPMO continues its work with LPJK to develop its plumbing certification criteria 23 - IAPMO reached a major milstone with the official annoucement of its Laboratory in Indonesia. Work is underway to prepare for its grand opening. 24 - See note 23
2016.04.26 | christopher.lindsay@iapmo.org | 2016.03.31 | 0 | 0 | 0 | 0 | 0 | 0 | 22 - IAPMO has scheduled its seocnd Train the Trainer session with Ministry officials. The training will take place in Q2 2016. Additionally, IAPMO continues its work with LPJK should finalize its review of IAPMO's plumbing personnel certification criteria shortly. 23 - IAPMO's is finalziing prepartation of its new testing and certification laboratory. The new lab should be opened in May 2016. 24 - See note 23
| christopher.lindsay@iapmo.org | 2016.06.30 | 0 | 0 | 0 | 0 | 0 | 0 | 21 - IAPMO has provide two train-the-trainer sessions to government officials who will be responsible for overseeign the enforcement of the new SNI 23 - This quarter IAPMO achieved a major milestone with the opening of its new product testing and certification laboratory in Jakarta. 24 - See note 23
| christopher.lindsay@iapmo.org | 2016.09.30 | 1 | 0 | 500 | 0 | 0 | 0 | 20 - All new Ministry of Public Works’ construction projects are now required to utilize SNI 8153:2015 for their plumbing systems. 22 - Early on in the project period, IAPMO pivoted away from the privately driven PEEP program in order to work with the Indonesia government in mandating new personnel certification criteria. That work is a key sustainable element of our project. However, IAPMO has trained more than 500+ people on the awareness of SNI 8153:2015 and importance of good plumbing systems to date. 23 - IAPMO's new laboratory in Indonesia is operational. It is scheduled to be assessed by KAN (Indonesia's accreditation body) in November 2016. After which it will be able to test and certify products to the Indonesian market. 24 - See Note 23.
|  |  | 1 | 5 | 500 | 0 | 0 | 10
As a percentage of goal during period: |  |  | 25% | 17.86% | 27.78% | 0% | 0% | 100%
Note on C1: Report results only for the current quarter. DO NOT CUMULATE RESULTS FROM PREVIOUS QUARTERS. Part B below is for reporting performance on measures designed by IAPMO specific to its 2013 MDCP project. Note that performance on ITA's primary metric, exports, is NOT reported in Part B. Report exports separately each quarter in Part A: field 6-export transations (goal for 2013.10.01-2015.06.30 is $3,083,298). Enter ONLY NUMBERS in fields 20-24 below. NOTES regarding numbers entered in fields 20-24 can be entered in field 40-Comments.
Note on A3: Enter the date that you completed the report for the quarter reported.
Note on B3: Email address of person completing report.
Note on C3: A quarter comprises three months or any portion thereof ending on March 31, June 30, September 30, or December 31. Enter, e.g. June 30,2013, as 06/30/2013. It will display as 2013.06.30.
Note on D3: IAPMO's long-term goal is 100% adoption of the Universal Plumbing Code for Indonesia (UPC-ID) across Indoneisa's 34 provinces. Within the project period, IAPMO has identified 4 major jurisdictions where adoption empahsis will be placed to facilitate further adoptions.
Note on E3: Number of educational institutions IAPMO has partnered with to provide Plumbing Education to Employment Program (PEEP) training. [Goal: 28 (2013=2, 2014=6, 2015=8, 2016=12)]
Note on F3: Number of students successfully completing Plumbing Education to Employment Program (PEEP) training. [Goal: 1800 (2013=0, 2014=400, 2015=600, 2016=800)]
Note on G3: Number of products certified through the certification lab. [Goal: 130 (2013=0, 2014=10, 2015=40, 2016=80)]
Note on H3: Number of US products certified through the certification lab--an indicator of success of US products in Indonesia. [Goal: 130 (2013=0, 2014=10, 2015=40, 2016=80)]
Note on I3: Number of identified major US developed product standards incporated into the new UPC-ID --a key market access requirement for plumbing products
Note on J3: If you need to explain any of the numbers reported in fields 20-22 enter text here preceded by the field number, e.g. "22-Consultations via email: 3, via telephone: 9"